## Template
Action plan template
Action | Owner | Due | Root cause | KPI

## Example
Action plan template
Action | Owner | Due | Root cause | KPI
Assign each new operator a fixed buddy on their own shift for the first eight weeks | Production manager | 2 June | The buddy changes with the shifts | Six-month attrition
Review each new operator’s progress every week against the training path | Training manager | 2 June | Each operator’s progress is not measured | Six-month attrition
Write a training path for each station, in the order the skills are learnt | Training manager | 16 June | No documented training path | Weeks to standard output
Set aside two hours of trainer time per shift in the production plan | Shift supervisor | 16 June | Trainers have no time set aside | Weeks to standard output
Reserve one practice station per line during training hours | Production manager | 30 June | Practice stations taken up by production | Weeks to standard output
Update the work instructions with two experienced operators | Process engineer | 14 July | Out-of-date work instructions | Weeks to standard output

## How to use
Free improvement action plan template for Excel
1. Start from the verified root causes
Write the root cause first, then the action that removes it. An action with no root cause behind it does not belong here.
2. Name one owner per action
A role or a person, never a department or a committee.
3. Agree the due date with the owner
A date the owner accepts. Long actions are split into steps with their own dates.
4. Link each action to a KPI and review weekly
The KPI shows whether the action worked. Late actions get a new date and a reason.
Full guide: https://leanos-app.com/en/recursos/plan-de-accion
https://leanos-app.com/en/recursos/plantillas/plan-de-accion